## Backlog
ID | Priority | Area/Application | UC | User Story ID | Title | Sprint | Acceptance Criteria / Comments
| 0 | 0 - General | - | G001 | Acceptance criteria common to all User Stories (US) of every sprint. | (All) | Development of every US should adopt (and if necessary revise) the domain model; Project documentation should be always available on the project repository ("docs" folder) and, when applicable, in accordance to the UML notation; The development process of every US (e.g.: analysis, design, testing, etc.) must be reported (as part of the documentation); The team should develop a relevant set of automated tests for every US / Class / Method.
| 1 | 0 - General | - | G002 | As Project Manager, I want the team to elaborate a Domain Model using DDD. | A
| 1 | 0 - General | - | G003 | As Project Manager, I want the team to configure the project repository. | A | The repository' name must follow the following template: "LEI21_22_S4_LabClass_TeamNumber". E.g. "LEI21_22_S4_2DA_01".
| 1 | 0 - General | - | G004 | As Project Manager, I want the team to configure the project structure to facilitate / accelerate the development of upcoming user stories. | A | By configuration, the system must support that data persistence is done either "in memory" or in a relational database (RDB). The system should have the ability to initialize some default data.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Quanto menor o número indicado, maior é a prioridade. Prioridade < 3 => Obrigatório. Prioridade = 3 => Obrigatório (em casos/grupos excepcionais pode ser apenas desejável) Prioridade > 3 => Desejável (em casos/grupos excepcionais pode ser obrigatório).

## Areas
Areas
0 - General
1 - Orders/Sales
2 - Warehouse
3 - Surveys
4 - AGV Management
5 - AGV Digital Twin
9 - Other

## Sheet1
1000
1001
1002
1003
1003
1004
1005
1006
2001
2002
2003
2010
2011
2012
2013
2014
2051
2052