## Backlog
ID | Priority | Area/Application | UC | User Story ID | Title | Sprint | Acceptance Criteria / Comments
| 0 | 0 - General | - | G001 | Acceptance criteria common to all User Stories (US) of every sprint. | (All) | Development of every US should adopt (and if necessary revise) the domain model; Project documentation should be always available on the project repository ("docs" folder) and, when applicable, in accordance to the UML notation; The development process of every US (e.g.: analysis, design, testing, etc.) must be reported (as part of the documentation); The team should develop a relevant set of automated tests for every US / Class / Method.
| 1 | 0 - General | - | G002 | As Project Manager, I want the team to elaborate a Domain Model using DDD. | A
| 1 | 0 - General | - | G003 | As Project Manager, I want the team to configure the project repository. | A | The repository' name must follow the following template: "LEI21_22_S4_LabClass_TeamNumber". E.g. "LEI21_22_S4_2DA_01".
| 1 | 0 - General | - | G004 | As Project Manager, I want the team to configure the project structure to facilitate / accelerate the development of upcoming user stories. | A | By configuration, the system must support that data persistence is done either "in memory" or in a relational database (RDB). The system should have the ability to initialize some default data.
| 1 | 0 - General | - | G004 | As Project Manager, I want the team to configure the project structure to facilitate / accelerate the development of upcoming user stories. | B | By configuration, the system must support that data persistence is done either "in memory" or in a relational database (RDB). The system should have the ability to initialize some default data.
Rui | 1 | 1 - Orders/Sales | 3.1.2a | 1001 | As Sales Clerk, I want to specify a new product for sale. | B
Rui | 1 | 1 - Orders/Sales | 3.1.3a | 1002 | As Sales Clerk, I want to view/search the products catalog. | B
Tiago | 1 | 1 - Orders/Sales | 3.1.4b | 1003 | As Sales Clerk, I want to register a new customer. | B
Tiago | 1 | 1 - Orders/Sales | 3.1.6a | 1004 | As Sales Clerk, I want to create a new products order on behalf of a given customer. | B
Hugo | 1 | 2 - Warehouse | 3.2.1 | 2001 | As Warehouse Employee, I want to set up the warehouse plant by uploading a JSON file. | B | Remark: a pre-defined JSON file can be automatically upload (e.g. at application start-up) to get a default warehouse plant and avoiding the employee to execute this action.
Tiago | 1 | 9 - Other | - | 9001 | As software product client, I want the team (software product supplier) to prepare a presentation focusing on the following aspects: (i) main objectives of the system; (ii) adopted development process and planning; (iii) teamwork methodology and conflict resolution strategy; (iv) product quality; (v) expected results; (vi) 'turnkey' format for software delivery/sale; among others relevant aspects. | B | The presentation can be prepared in any digital support considered as appropriate (e.g. powerpoint) and whose resulting artifact can be deliverable.
Tiago | 3 | 1 - Orders/Sales | - | 1900 | As Project Manager, I intend that, for demonstration purposes, the system has the possibility of being initialized (bootstrap) with some information related to the product catalog and auxiliary information (e.g., categories of products). | B | Bootstrap.
Hugo | 3 | 2 - Warehouse | 3.2.2 | 2002 | As Warehouse Employee, I want to configure the AGVs available on the warehouse. | B
Tiago | 5 | 1 - Orders/Sales | 3.1.1 | 1005 | As Sales Clerk, I want to define a new category of products. | B
| 1 | 2 - Warehouse | 3.2.4b | 2003 | As Warehouse Employee, I want to access the list of orders that need to be prepared by an AGV and be able to ask/force any of those orders to be immediately prepared by an AGV available. | C
| 1 | 3 - Surveys | 3.3.1 | 3000 | As Project Manager, I want the team to specify a grammar allowing to express several kinds of questionnaires. | C | The grammar should be conceived having in mind its reusability/applicability on other application domains than the one of this project (e.g., pedagogical questionnaires).
| 1 | 3 - Surveys | 3.3.1 | 3001 | As Sales Manager, I want to create a new questionnaire to be further answered by customers meeting the specified criteria (e.g.: have ordered a given product; belong to a given age group). | C | The set of questions/answers composing the questionnaire should be expressed and validated (parsed) using the grammar being developed for this purpose.
| 1 | 4 - AGV Management | - | 4001 | As Project Manager, I want that the "AGVManager" component supports properly, at request, the needs of the "BackOfficeApp" application as well as the needs the AGV digital twin. | C | It must be used the provided application protocol (SPOMS2022). It is suggested the adoptiong of concurrent mechanisms (e.g. threads) and state sharing between these mechanisms.
| 1 | 4 - AGV Management | 3.2.4a | 4002 | As Project Manager, I want that the "AGVManager" component is enhanced with a basic FIFO algorithm to automatically assign tasks to AGVs. | C
| 1 | 5 - AGV Digital Twin | - | 5001 | As Project Manager, I want that the team start developing the input communication module of the AGV digital twin to accept requests from the "AGVManager". | C | It must be used the provided application protocol (SPOMS2022). It is suggested the adoptiong of concurrent mechanisms (e.g. threads) and state sharing between these mechanisms. In this sprint, for demonstration purposes, it is acceptable to mock processing some of the incoming requests to foster some output communication.
| 1 | 5 - AGV Digital Twin | - | 5002 | As Project Manager, I want that the team start developing the output communication module of the AGV digital twin to update its status on the "AGVManager". | C | It must be used the provided application protocol (SPOMS2022). It is suggested the adoptiong of concurrent mechanisms (e.g. threads) and state sharing between these mechanisms. In this sprint, for demonstration purposes, it is acceptable to mock processing some of the incoming requests to foster some output communication.
| 3 | 2 - Warehouse | 3.2.5 | 2004 | As Warehouse Employee, I want to access the list of orders that have already been prepared by the AGVs and be able to update any of those orders as having been dispatched for customer delivery. | C
| 3 | 2 - Warehouse | 3.2.3 | 2005 | As Warehouse Employee, I want to open a web dashboard presenting the current status of the AGVs as well as their position in the warehouse layout and keeps updated automatically (e.g.: at each minute). | C | It must be used the provided application protocol (SPOMS2022). The dashboard is intended to be displayed on a web page provided by an existing HTTP server in the "BackOfficeApp" application and only available to localhost. The dashboard web page is kept updated without reloading.
| 5 | 1 - Orders/Sales | 3.1.3a/c | 1501 | As Customer, I want to view/search the product catalog and be able to add a product to the shopping cart. | C | It is mandatory using the "OrdersServer" component (cf. US1901).
| 5 | 1 - Orders/Sales | - | 1901 | As Project Manager, I want that the "OrdersServer" component supports properly, at request, the needs of the "CustomerApp" application. | C | It must be used the provided application protocol (SPOMS2022). It is suggested the adoptiong of concurrent mechanisms (e.g. threads) and state sharing between these mechanisms. In this sprint, for demonstration purposes, it is acceptable to mock processing some of the incoming requests.
| 1 | 3 - Surveys | 3.3.4 | 3002 | As Sales Manager, I want to get a statistical report regarding a previously set up questionnaire. | D | Again, notice that the report should be generated considering the given questionnaire and the set of answers obtained until the current moment.
| 1 | 3 - Surveys | 3.3.2-3 | 3501 | As Customer, I want to get the list of questionnaires that the system is asking me to answer and be able to answer any of those questionnaires. | D | Notice that the UI should be generated dynamically in accordance to the given questionnaire. I.e. que UI is generated by interpreting the input questionnaire. The answers should be saved in a raw text format to be further processed/analyzed.
| 1 | 4 - AGV Management | - | 4003 | As Project Manager, I want the communications (of the AGVManager) made through the SPOMS2022 protocol to be secured/protected. | D | It should be adopted SSL/TLS with mutual authentication based on public key certificates. It complements the US4001.
| 1 | 5 - AGV Digital Twin | - | 5003 | As Project Manager, I want the input communications (of the AGV Digital Twin) made through the SPOMS2022 protocol to be secured/protected. | D | It should be adopted SSL/TLS with mutual authentication based on public key certificates. It complements the US5001.
| 1 | 5 - AGV Digital Twin | - | 5004 | As Project Manager, I want the output communications (of the AGV Digital Twin) made through the SPOMS2022 protocol to be secured/protected. | D | It should be adopted SSL/TLS with mutual authentication based on public key certificates. It complements the US5002.
| 1 | 5 - AGV Digital Twin | - | 5100 | As Project Manager, I want that the team to develop and integrate the others components/parts of the AGV digital twin (e.g.: movement, obstacle sensors, control unit). | D | In conformity with SCOMP guidelines.
| 1 | 9 - Other | - | 9002 | As Software Product Client, I want the team (software supplier) to prepare a presentation focusing on the following aspects: (i) results achieved; (ii) critical analysis of results and teamwork, adopting the SWOT format; (iii) evidence of applying the software engineering/development process; (iv) the deployment scenario of the solution; (v) the quality of the final product; (vi) suggestions of improvement; among others relevant aspects. It is also intended that each student present a self-assessment regarding their technical and behavioral skills before and after carrying out the integrative project. The result must be included in a table/graph containing all the elements of the group. We suggest the adoption of a simple rating scale (e.g. very weak, weak, fair, good, very good, excellent). | D | The presentation can be prepared in any digital support considered as appropriate (e.g. powerpoint) and whose resulting artifact can be deliverable. This presentation should be complemented with a demonstration to the customer showing the the system in operation.
| 3 | 1 - Orders/Sales | 3.1.7b | 1006 | As Sales Clerk, I want to access a list of orders that had been dispatched for customer delivery and be able to update some of those orders to as being delivered. | D
| 3 | 2 - Warehouse | - | 2006 | As Project Manager, I want the communications made through the SPOMS2022 protocol to be secured/protected. | D | It should be adopted SSL/TLS with mutual authentication based on public key certificates. It complements the US2005.
| 5 | 1 - Orders/Sales | 3.1.8a | 1502 | As Customer, I want to view/check the status of my open orders. | D | It is mandatory using the "OrdersServer" component (cf. US1901).
| 5 | 1 - Orders/Sales | - | 1902 | As Project Manager, I want the communications made through the SPOMS2022 protocol to be secured/protected. | D | It should be adopted SSL/TLS with mutual authentication based on public key certificates. It complements the US1901.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Quanto menor o número indicado, maior é a prioridade. Prioridade < 3 => Obrigatório. Prioridade = 3 => Obrigatório (em casos/grupos excepcionais pode ser apenas desejável) Prioridade > 3 => Desejável (em casos/grupos excepcionais pode ser obrigatório).
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incompleta no Sprint A e continua no Sprint B

## Areas
Areas
0 - General
1 - Orders/Sales
2 - Warehouse
3 - Surveys
4 - AGV Management
5 - AGV Digital Twin
9 - Other

## Sheet1
1000
1001
1002
1003
1003
1004
1005
1006
2001
2002
2003
2010
2011
2012
2013
2014
2051
2052